# Project Sunrise

A second Aurora café on the Korenmarkt, Ghent — proposal for the board

Prepared by Lena Verhoeven · 12 October 2026 · Version 1.2

# Summary

Our Vrijdagmarkt café has run at full capacity on weekends for eighteen months. We propose opening a second, larger café of 80 seats on the Korenmarkt in May 2027, with an investment of € 122,650 and a break-even point in month 14.

# Why now

- Weekend queues average 22 minutes; we turn away an estimated 300 guests a week.

- Wholesale roasting volume grew 38 % this year, so the new café doubles as a tasting room.

- The Korenmarkt lease is available at € 4,200 a month, 9 % below comparable units.

# The plan

## Location and format

A ground-floor unit of 160 m² with a terrace for 24. The front third is a fast counter for take-away; the back is a seated café with a visible roaster and a small retail wall for beans and brewing gear.

## Timeline

- Sign the lease and order the espresso machine (January 2027).

- Fit-out, permits and hiring (February to April 2027).

- Soft opening for regulars and neighbours (late April 2027).

- Public opening (1 May 2027).

# Budget

Opening investment by quarter. Running costs are in the Project Sunrise Budget workbook.

| Item | Q1 2027 | Q2 2027 | Total |
| --- | --- | --- | --- |
| Fit-out and furniture | € 48,000 | € 6,000 | € 54,000 |
| Espresso machine and grinders | € 22,500 | – | € 22,500 |
| Staff hiring and training | € 9,000 | € 14,000 | € 23,000 |
| Opening marketing | € 3,500 | € 8,500 | € 12,000 |
| Contingency (10 %) | € 8,300 | € 2,850 | € 11,150 |
| Total | € 91,300 | € 31,350 | € 122,650 |

Totals exclude VAT. Contingency is 10 % of each quarter's other costs.

# Risks

- Construction delay. Mitigated by a fixed-price fit-out contract with a late-delivery penalty.

- Slower ramp-up. The budget assumes 55 % of Vrijdagmarkt's covers in month one, rising to 90 % by month six.

- Staffing. We start recruiting baristas in February and train them in the existing café.

# Decision requested

Approve the investment of € 122,650 and authorise the lease signature before 15 December 2026.